## Cost
Please insert Project's Information
The project begins from the chainage: |  |  | 5000 | (in m)
and Project finishes at the chainage: |  |  | 15000 | (in m)
The project's intervals for the excavations calculations are (advancement rate): |  |  |  | 100
The daily hours of work are: |  |  | 8
In the following table, insert the quantities for each construction work (m3)
Total project's quantities
excavations |  | embankments | sod land |  | pavement | asphalt
appropriate (m3) | inappropriate (m3) | m3 | excavations (m3) | sod land (m3) | m3 | m3
56786 | 3456 | 87656 | 568765 | 3456 | 87654 | 98765
Insert the number of the available consrtuction equipment on site in the following table
Construction Equipment
Equipment |  | Use |  |  | Number
Excavators |  | excvations |  |  | 2
Loaders |  | earthworks |  |  | 2
Trucks |  | transportation |  |  | 15
Pavement Trucks |  |  |  |  | 8
Asphalt Trucks |  |  |  |  | 6
Pavers |  | compaction |  |  | 6
Finisher |  | paving |  |  | 2
Water Tanks |  | water supply on site |  |  | 2
Fuel Tanks |  | fuel supply on site |  |  | 2
In the following two tables insert the production rate for the equipment (m3/h) and the fuel consumption (l/h). The fuel supply is made on site by fuels tanks .
Equipment production rate (m3/h) |  |  |  | Fuel consumption (l/h)
Excavator |  | 50 |  | Excavator |  |  | 40
Loader |  | 90 |  | Loaders |  |  | 60
Paver |  | 500 |  | Pavers |  |  | 25
Finisher |  | 300 |  | Finisher |  |  | 25
For Trucks and Tanks insert thei volumes' capacity (m3), their fule consumption (l/100 km) and their velocity (km/h). The max velocity is when the Trucks are empty, whereas the min velocity when Trucks are loaded.
Volumes (m3)
Trucks |  | 14 |  | Equipment | Consumption (l/100 km) |  | Velocity (km/h)
Paver Trucks |  | 14 |  |  |  |  | max | min
Asphalt Trucks |  | 14 |  | Trucks | 60 |  | 80 | 35
Water Tanks |  | 10 |  | Tanks | 40 |  | 80 | 50
Fuel Tanks |  | 10
The fuel price is estimated at: |  |  |  | 1.5 | €/l
The daily wage of the operator is: |  |  | 80 | €
The automated calculation of the site location with the minimum operation cost for the transportation and operation of the equipment. The quantities are divided equally for all the project legnth.
Clarifications
→ The optimum site location is presented in transportation column, "the otimum site location"
→ For the calulation of the cost at this location it is necassary to insert the location in the respective cell. This algoritm is better applied for linear projects with a totla length no more than 10km.
→ The site cost is appeared in the column "Cost"
→ This algoritm is based only on the quantitative characteristics of the project. For this location to be chosen the qualitative characteristics of this should be taken into account. The qualitative characteristics include the followings:
❶Morfology and quality of ground
❷Ground slope (places with slopes greater than 17% are rejected)
❸Physical factors (temperature, humidity, sun, rain)
❹Available space for the size of the construction site
❺Available water supply, electricity, sewerage
❻Legislation (land uses, biodiversity, archeology)
Since all the criteria are met then the location is chosen, otherwise it is investigated a location near the proposed.
CALCULATION OF THE OPTIMUM SITE LOCATION
Total project length |  | 10000
Intervals |  | 100
Production rate/day |  |  |  | Fuel consumption (l/day)
Excavators |  | 800 |  | Excavators |  |  | 320
Loaders |  | 1440 |  | Loaders |  |  | 480
Pavers |  | 24000 |  | Pavers |  |  | 200
Finisher |  | 4800 |  | Finisher |  |  | 200
[33 empty] | Cost |  |  |  |  | Cost ↓
[33 empty] | Trucks |  | Tanks
|  | excavations |  | embankments | tranportaions of eartworks | earthworks supply | sod land |  | earthworks transportation | earthworks supply | pavement | asphalt |  | Total Fuel Consuption (m3) |  |  |  |  | Number of Necessary Trasportations |  |  |  |  | Total Tranportations |  | Total trasportations | Half trasportations | Optimum Site Location ↓ | Please insert the optimum site location for the cost calculation |  |  | Distance from site | Fuel cost | Wages | Fuel cost | Wages | sum
Intervals | Chainage | appropriate (m3) | inappropriate (m3) | m3 | m3 | m3 | excavations (m3) | sod land (m3) | m3 | m3 | m3 | m3 |  | Excavators | Loaders | Pavers | Finisher |  | Earthworks Trucks | Pavement Trucks | Asphalt Trucks | Water Tanks | Fuel Tanks | Trucks | Tanks
1 | 5100 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 5100 | 5.12 | 4.8 | 1.2 | 0.4 | 5100 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 1130 |  |  | X= | 10000 | 5100 | 4900 | 4948.02 | 1129.0125 | 23.52 | 6.37 | 6106.9225
2 | 5200 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 5200 | 5.12 | 4.8 | 1.2 | 0.4 | 5200 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 2260 |  |  |  |  | 5200 | 4800 | 4847.04 | 1105.9714 | 23.04 | 6.24 | 12089.2139
3 | 5300 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 5300 | 5.12 | 4.8 | 1.2 | 0.4 | 5300 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 3390 |  |  |  |  | 5300 | 4700 | 4746.06 | 1082.9304 | 22.56 | 6.11 | 17946.8743
4 | 5400 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 5400 | 5.12 | 4.8 | 1.2 | 0.4 | 5400 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 4520 |  |  |  |  | 5400 | 4600 | 4645.08 | 1059.8893 | 22.08 | 5.98 | 23679.9036
5 | 5500 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 5500 | 5.12 | 4.8 | 1.2 | 0.4 | 5500 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 5650 |  |  |  |  | 5500 | 4500 | 4544.1 | 1036.8482 | 21.6 | 5.85 | 29288.3018
6 | 5600 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 5600 | 5.12 | 4.8 | 1.2 | 0.4 | 5600 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 6780 |  |  |  |  | 5600 | 4400 | 4443.12 | 1013.8071 | 21.12 | 5.72 | 34772.0689
7 | 5700 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 5700 | 5.12 | 4.8 | 1.2 | 0.4 | 5700 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 7910 |  |  |  |  | 5700 | 4300 | 4342.14 | 990.7661 | 20.64 | 5.59 | 40131.205
8 | 5800 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 5800 | 5.12 | 4.8 | 1.2 | 0.4 | 5800 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 9040 |  |  |  |  | 5800 | 4200 | 4241.16 | 967.725 | 20.16 | 5.46 | 45365.71
9 | 5900 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 5900 | 5.12 | 4.8 | 1.2 | 0.4 | 5900 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 10170 |  |  |  |  | 5900 | 4100 | 4140.18 | 944.6839 | 19.68 | 5.33 | 50475.5839
10 | 6000 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 6000 | 5.12 | 4.8 | 1.2 | 0.4 | 6000 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 11300 |  |  |  |  | 6000 | 4000 | 4039.2 | 921.6429 | 19.2 | 5.2 | 55460.8268
11 | 6100 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 6100 | 5.12 | 4.8 | 1.2 | 0.4 | 6100 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 12430 |  |  |  |  | 6100 | 3900 | 3938.22 | 898.6018 | 18.72 | 5.07 | 60321.4386
12 | 6200 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 6200 | 5.12 | 4.8 | 1.2 | 0.4 | 6200 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 13560 |  |  |  |  | 6200 | 3800 | 3837.24 | 875.5607 | 18.24 | 4.94 | 65057.4193
13 | 6300 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 6300 | 5.12 | 4.8 | 1.2 | 0.4 | 6300 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 14690 |  |  |  |  | 6300 | 3700 | 3736.26 | 852.5196 | 17.76 | 4.81 | 69668.7689
14 | 6400 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 6400 | 5.12 | 4.8 | 1.2 | 0.4 | 6400 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 15820 |  |  |  |  | 6400 | 3600 | 3635.28 | 829.4786 | 17.28 | 4.68 | 74155.4875
15 | 6500 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 6500 | 5.12 | 4.8 | 1.2 | 0.4 | 6500 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 16950 |  |  |  |  | 6500 | 3500 | 3534.3 | 806.4375 | 16.8 | 4.55 | 78517.575
16 | 6600 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 6600 | 5.12 | 4.8 | 1.2 | 0.4 | 6600 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 18080 |  |  |  |  | 6600 | 3400 | 3433.32 | 783.3964 | 16.32 | 4.42 | 82755.0314
17 | 6700 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 6700 | 5.12 | 4.8 | 1.2 | 0.4 | 6700 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 19210 |  |  |  |  | 6700 | 3300 | 3332.34 | 760.3554 | 15.84 | 4.29 | 86867.8568
18 | 6800 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 6800 | 5.12 | 4.8 | 1.2 | 0.4 | 6800 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 20340 |  |  |  |  | 6800 | 3200 | 3231.36 | 737.3143 | 15.36 | 4.16 | 90856.0511
19 | 6900 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 6900 | 5.12 | 4.8 | 1.2 | 0.4 | 6900 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 21470 |  |  |  |  | 6900 | 3100 | 3130.38 | 714.2732 | 14.88 | 4.03 | 94719.6143
20 | 7000 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 7000 | 5.12 | 4.8 | 1.2 | 0.4 | 7000 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 22600 |  |  |  |  | 7000 | 3000 | 3029.4 | 691.2321 | 14.4 | 3.9 | 98458.5464
21 | 7100 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 7100 | 5.12 | 4.8 | 1.2 | 0.4 | 7100 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 23730 |  |  |  |  | 7100 | 2900 | 2928.42 | 668.1911 | 13.92 | 3.77 | 102072.8475
22 | 7200 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 7200 | 5.12 | 4.8 | 1.2 | 0.4 | 7200 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 24860 |  |  |  |  | 7200 | 2800 | 2827.44 | 645.15 | 13.44 | 3.64 | 105562.5175
23 | 7300 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 7300 | 5.12 | 4.8 | 1.2 | 0.4 | 7300 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 25990 |  |  |  |  | 7300 | 2700 | 2726.46 | 622.1089 | 12.96 | 3.51 | 108927.5564
24 | 7400 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 7400 | 5.12 | 4.8 | 1.2 | 0.4 | 7400 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 27120 |  |  |  |  | 7400 | 2600 | 2625.48 | 599.0679 | 12.48 | 3.38 | 112167.9643
25 | 7500 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 7500 | 5.12 | 4.8 | 1.2 | 0.4 | 7500 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 28250 |  |  |  |  | 7500 | 2500 | 2524.5 | 576.0268 | 12 | 3.25 | 115283.7411
26 | 7600 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 7600 | 5.12 | 4.8 | 1.2 | 0.4 | 7600 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 29380 |  |  |  |  | 7600 | 2400 | 2423.52 | 552.9857 | 11.52 | 3.12 | 118274.8868
27 | 7700 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 7700 | 5.12 | 4.8 | 1.2 | 0.4 | 7700 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 30510 |  |  |  |  | 7700 | 2300 | 2322.54 | 529.9446 | 11.04 | 2.99 | 121141.4014
28 | 7800 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 7800 | 5.12 | 4.8 | 1.2 | 0.4 | 7800 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 31640 |  |  |  |  | 7800 | 2200 | 2221.56 | 506.9036 | 10.56 | 2.86 | 123883.285
29 | 7900 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 7900 | 5.12 | 4.8 | 1.2 | 0.4 | 7900 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 32770 |  |  |  |  | 7900 | 2100 | 2120.58 | 483.8625 | 10.08 | 2.73 | 126500.5375
30 | 8000 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 8000 | 5.12 | 4.8 | 1.2 | 0.4 | 8000 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 33900 |  |  |  |  | 8000 | 2000 | 2019.6 | 460.8214 | 9.6 | 2.6 | 128993.1589
31 | 8100 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 8100 | 5.12 | 4.8 | 1.2 | 0.4 | 8100 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 35030 |  |  |  |  | 8100 | 1900 | 1918.62 | 437.7804 | 9.12 | 2.47 | 131361.1493
32 | 8200 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 8200 | 5.12 | 4.8 | 1.2 | 0.4 | 8200 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 36160 |  |  |  |  | 8200 | 1800 | 1817.64 | 414.7393 | 8.64 | 2.34 | 133604.5086
33 | 8300 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 8300 | 5.12 | 4.8 | 1.2 | 0.4 | 8300 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 37290 |  |  |  |  | 8300 | 1700 | 1716.66 | 391.6982 | 8.16 | 2.21 | 135723.2368
34 | 8400 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 8400 | 5.12 | 4.8 | 1.2 | 0.4 | 8400 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 38420 |  |  |  |  | 8400 | 1600 | 1615.68 | 368.6571 | 7.68 | 2.08 | 137717.3339
35 | 8500 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 8500 | 5.12 | 4.8 | 1.2 | 0.4 | 8500 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 39550 |  |  |  |  | 8500 | 1500 | 1514.7 | 345.6161 | 7.2 | 1.95 | 139586.8
36 | 8600 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 8600 | 5.12 | 4.8 | 1.2 | 0.4 | 8600 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 40680 |  |  |  |  | 8600 | 1400 | 1413.72 | 322.575 | 6.72 | 1.82 | 141331.635
37 | 8700 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 8700 | 5.12 | 4.8 | 1.2 | 0.4 | 8700 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 41810 |  |  |  |  | 8700 | 1300 | 1312.74 | 299.5339 | 6.24 | 1.69 | 142951.8389
38 | 8800 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 8800 | 5.12 | 4.8 | 1.2 | 0.4 | 8800 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 42940 |  |  |  |  | 8800 | 1200 | 1211.76 | 276.4929 | 5.76 | 1.56 | 144447.4118
39 | 8900 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 8900 | 5.12 | 4.8 | 1.2 | 0.4 | 8900 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 44070 |  |  |  |  | 8900 | 1100 | 1110.78 | 253.4518 | 5.28 | 1.43 | 145818.3536
40 | 9000 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 9000 | 5.12 | 4.8 | 1.2 | 0.4 | 9000 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 45200 |  |  |  |  | 9000 | 1000 | 1009.8 | 230.4107 | 4.8 | 1.3 | 147064.6643
41 | 9100 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 9100 | 5.12 | 4.8 | 1.2 | 0.4 | 9100 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 46330 |  |  |  |  | 9100 | 900 | 908.82 | 207.3696 | 4.32 | 1.17 | 148186.3439
42 | 9200 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 9200 | 5.12 | 4.8 | 1.2 | 0.4 | 9200 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 47460 |  |  |  |  | 9200 | 800 | 807.84 | 184.3286 | 3.84 | 1.04 | 149183.3925
43 | 9300 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 9300 | 5.12 | 4.8 | 1.2 | 0.4 | 9300 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 48590 |  |  |  |  | 9300 | 700 | 706.86 | 161.2875 | 3.36 | 0.91 | 150055.81
44 | 9400 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 9400 | 5.12 | 4.8 | 1.2 | 0.4 | 9400 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 49720 |  |  |  |  | 9400 | 600 | 605.88 | 138.2464 | 2.88 | 0.78 | 150803.5964
45 | 9500 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 9500 | 5.12 | 4.8 | 1.2 | 0.4 | 9500 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 50850 |  |  |  |  | 9500 | 500 | 504.9 | 115.2054 | 2.4 | 0.65 | 151426.7518
46 | 9600 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 9600 | 5.12 | 4.8 | 1.2 | 0.4 | 9600 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 51980 |  |  |  |  | 9600 | 400 | 403.92 | 92.1643 | 1.92 | 0.52 | 151925.2761
47 | 9700 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 9700 | 5.12 | 4.8 | 1.2 | 0.4 | 9700 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 53110 |  |  |  |  | 9700 | 300 | 302.94 | 69.1232 | 1.44 | 0.39 | 152299.1693
48 | 9800 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 9800 | 5.12 | 4.8 | 1.2 | 0.4 | 9800 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 54240 |  |  |  |  | 9800 | 200 | 201.96 | 46.0821 | 0.96 | 0.26 | 152548.4314
49 | 9900 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 9900 | 5.12 | 4.8 | 1.2 | 0.4 | 9900 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 55370 |  |  |  |  | 9900 | 100 | 100.98 | 23.0411 | 0.48 | 0.13 | 152673.0625
50 | 10000 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 10000 | 5.12 | 4.8 | 1.2 | 0.4 | 10000 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 56500 |  | 10000 |  |  | 10000 | 0 | 0 | 0 | 0 | 0 | 152673.0625
51 | 10100 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 10100 | 5.12 | 4.8 | 1.2 | 0.4 | 10100 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 57630 |  |  |  |  | 10100 | 100 | 100.98 | 23.0411 | 0.48 | 0.13 | 152797.6936
52 | 10200 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 10200 | 5.12 | 4.8 | 1.2 | 0.4 | 10200 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 58760 |  |  |  |  | 10200 | 200 | 201.96 | 46.0821 | 0.96 | 0.26 | 153046.9557
53 | 10300 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 10300 | 5.12 | 4.8 | 1.2 | 0.4 | 10300 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 59890 |  |  |  |  | 10300 | 300 | 302.94 | 69.1232 | 1.44 | 0.39 | 153420.8489
54 | 10400 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 10400 | 5.12 | 4.8 | 1.2 | 0.4 | 10400 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 61020 |  |  |  |  | 10400 | 400 | 403.92 | 92.1643 | 1.92 | 0.52 | 153919.3732
55 | 10500 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 10500 | 5.12 | 4.8 | 1.2 | 0.4 | 10500 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 62150 |  |  |  |  | 10500 | 500 | 504.9 | 115.2054 | 2.4 | 0.65 | 154542.5286
56 | 10600 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 10600 | 5.12 | 4.8 | 1.2 | 0.4 | 10600 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 63280 |  |  |  |  | 10600 | 600 | 605.88 | 138.2464 | 2.88 | 0.78 | 155290.315
57 | 10700 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 10700 | 5.12 | 4.8 | 1.2 | 0.4 | 10700 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 64410 |  |  |  |  | 10700 | 700 | 706.86 | 161.2875 | 3.36 | 0.91 | 156162.7325
58 | 10800 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 10800 | 5.12 | 4.8 | 1.2 | 0.4 | 10800 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 65540 |  |  |  |  | 10800 | 800 | 807.84 | 184.3286 | 3.84 | 1.04 | 157159.7811
59 | 10900 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 10900 | 5.12 | 4.8 | 1.2 | 0.4 | 10900 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 66670 |  |  |  |  | 10900 | 900 | 908.82 | 207.3696 | 4.32 | 1.17 | 158281.4607
60 | 11000 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 11000 | 5.12 | 4.8 | 1.2 | 0.4 | 11000 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 67800 |  |  |  |  | 11000 | 1000 | 1009.8 | 230.4107 | 4.8 | 1.3 | 159527.7714
61 | 11100 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 11100 | 5.12 | 4.8 | 1.2 | 0.4 | 11100 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 68930 |  |  |  |  | 11100 | 1100 | 1110.78 | 253.4518 | 5.28 | 1.43 | 160898.7132
62 | 11200 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 11200 | 5.12 | 4.8 | 1.2 | 0.4 | 11200 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 70060 |  |  |  |  | 11200 | 1200 | 1211.76 | 276.4929 | 5.76 | 1.56 | 162394.2861
63 | 11300 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 11300 | 5.12 | 4.8 | 1.2 | 0.4 | 11300 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 71190 |  |  |  |  | 11300 | 1300 | 1312.74 | 299.5339 | 6.24 | 1.69 | 164014.49
64 | 11400 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 11400 | 5.12 | 4.8 | 1.2 | 0.4 | 11400 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 72320 |  |  |  |  | 11400 | 1400 | 1413.72 | 322.575 | 6.72 | 1.82 | 165759.325
65 | 11500 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 11500 | 5.12 | 4.8 | 1.2 | 0.4 | 11500 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 73450 |  |  |  |  | 11500 | 1500 | 1514.7 | 345.6161 | 7.2 | 1.95 | 167628.7911
66 | 11600 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 11600 | 5.12 | 4.8 | 1.2 | 0.4 | 11600 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 74580 |  |  |  |  | 11600 | 1600 | 1615.68 | 368.6571 | 7.68 | 2.08 | 169622.8882
67 | 11700 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 11700 | 5.12 | 4.8 | 1.2 | 0.4 | 11700 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 75710 |  |  |  |  | 11700 | 1700 | 1716.66 | 391.6982 | 8.16 | 2.21 | 171741.6164
68 | 11800 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 11800 | 5.12 | 4.8 | 1.2 | 0.4 | 11800 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 76840 |  |  |  |  | 11800 | 1800 | 1817.64 | 414.7393 | 8.64 | 2.34 | 173984.9757
69 | 11900 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 11900 | 5.12 | 4.8 | 1.2 | 0.4 | 11900 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 77970 |  |  |  |  | 11900 | 1900 | 1918.62 | 437.7804 | 9.12 | 2.47 | 176352.9661
70 | 12000 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 12000 | 5.12 | 4.8 | 1.2 | 0.4 | 12000 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 79100 |  |  |  |  | 12000 | 2000 | 2019.6 | 460.8214 | 9.6 | 2.6 | 178845.5875
71 | 12100 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 12100 | 5.12 | 4.8 | 1.2 | 0.4 | 12100 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 80230 |  |  |  |  | 12100 | 2100 | 2120.58 | 483.8625 | 10.08 | 2.73 | 181462.84
72 | 12200 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 12200 | 5.12 | 4.8 | 1.2 | 0.4 | 12200 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 81360 |  |  |  |  | 12200 | 2200 | 2221.56 | 506.9036 | 10.56 | 2.86 | 184204.7236
73 | 12300 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 12300 | 5.12 | 4.8 | 1.2 | 0.4 | 12300 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 82490 |  |  |  |  | 12300 | 2300 | 2322.54 | 529.9446 | 11.04 | 2.99 | 187071.2382
74 | 12400 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 12400 | 5.12 | 4.8 | 1.2 | 0.4 | 12400 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 83620 |  |  |  |  | 12400 | 2400 | 2423.52 | 552.9857 | 11.52 | 3.12 | 190062.3839
75 | 12500 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 12500 | 5.12 | 4.8 | 1.2 | 0.4 | 12500 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 84750 |  |  |  |  | 12500 | 2500 | 2524.5 | 576.0268 | 12 | 3.25 | 193178.1607
76 | 12600 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 12600 | 5.12 | 4.8 | 1.2 | 0.4 | 12600 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 85880 |  |  |  |  | 12600 | 2600 | 2625.48 | 599.0679 | 12.48 | 3.38 | 196418.5686
77 | 12700 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 12700 | 5.12 | 4.8 | 1.2 | 0.4 | 12700 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 87010 |  |  |  |  | 12700 | 2700 | 2726.46 | 622.1089 | 12.96 | 3.51 | 199783.6075
78 | 12800 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 12800 | 5.12 | 4.8 | 1.2 | 0.4 | 12800 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 88140 |  |  |  |  | 12800 | 2800 | 2827.44 | 645.15 | 13.44 | 3.64 | 203273.2775
79 | 12900 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 12900 | 5.12 | 4.8 | 1.2 | 0.4 | 12900 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 89270 |  |  |  |  | 12900 | 2900 | 2928.42 | 668.1911 | 13.92 | 3.77 | 206887.5786
80 | 13000 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 13000 | 5.12 | 4.8 | 1.2 | 0.4 | 13000 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 90400 |  |  |  |  | 13000 | 3000 | 3029.4 | 691.2321 | 14.4 | 3.9 | 210626.5107
81 | 13100 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 13100 | 5.12 | 4.8 | 1.2 | 0.4 | 13100 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 91530 |  |  |  |  | 13100 | 3100 | 3130.38 | 714.2732 | 14.88 | 4.03 | 214490.0739
82 | 13200 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 13200 | 5.12 | 4.8 | 1.2 | 0.4 | 13200 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 92660 |  |  |  |  | 13200 | 3200 | 3231.36 | 737.3143 | 15.36 | 4.16 | 218478.2682
83 | 13300 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 13300 | 5.12 | 4.8 | 1.2 | 0.4 | 13300 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 93790 |  |  |  |  | 13300 | 3300 | 3332.34 | 760.3554 | 15.84 | 4.29 | 222591.0936
84 | 13400 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 13400 | 5.12 | 4.8 | 1.2 | 0.4 | 13400 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 94920 |  |  |  |  | 13400 | 3400 | 3433.32 | 783.3964 | 16.32 | 4.42 | 226828.55
85 | 13500 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 13500 | 5.12 | 4.8 | 1.2 | 0.4 | 13500 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 96050 |  |  |  |  | 13500 | 3500 | 3534.3 | 806.4375 | 16.8 | 4.55 | 231190.6375
86 | 13600 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 13600 | 5.12 | 4.8 | 1.2 | 0.4 | 13600 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 97180 |  |  |  |  | 13600 | 3600 | 3635.28 | 829.4786 | 17.28 | 4.68 | 235677.3561
87 | 13700 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 13700 | 5.12 | 4.8 | 1.2 | 0.4 | 13700 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 98310 |  |  |  |  | 13700 | 3700 | 3736.26 | 852.5196 | 17.76 | 4.81 | 240288.7057
88 | 13800 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 13800 | 5.12 | 4.8 | 1.2 | 0.4 | 13800 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 99440 |  |  |  |  | 13800 | 3800 | 3837.24 | 875.5607 | 18.24 | 4.94 | 245024.6864
89 | 13900 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 13900 | 5.12 | 4.8 | 1.2 | 0.4 | 13900 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 100570 |  |  |  |  | 13900 | 3900 | 3938.22 | 898.6018 | 18.72 | 5.07 | 249885.2982
90 | 14000 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 14000 | 5.12 | 4.8 | 1.2 | 0.4 | 14000 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 101700 |  |  |  |  | 14000 | 4000 | 4039.2 | 921.6429 | 19.2 | 5.2 | 254870.5411
91 | 14100 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 14100 | 5.12 | 4.8 | 1.2 | 0.4 | 14100 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 102830 |  |  |  |  | 14100 | 4100 | 4140.18 | 944.6839 | 19.68 | 5.33 | 259980.415
92 | 14200 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 14200 | 5.12 | 4.8 | 1.2 | 0.4 | 14200 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 103960 |  |  |  |  | 14200 | 4200 | 4241.16 | 967.725 | 20.16 | 5.46 | 265214.92
93 | 14300 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 14300 | 5.12 | 4.8 | 1.2 | 0.4 | 14300 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 105090 |  |  |  |  | 14300 | 4300 | 4342.14 | 990.7661 | 20.64 | 5.59 | 270574.0561
94 | 14400 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 14400 | 5.12 | 4.8 | 1.2 | 0.4 | 14400 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 106220 |  |  |  |  | 14400 | 4400 | 4443.12 | 1013.8071 | 21.12 | 5.72 | 276057.8232
95 | 14500 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 14500 | 5.12 | 4.8 | 1.2 | 0.4 | 14500 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 107350 |  |  |  |  | 14500 | 4500 | 4544.1 | 1036.8482 | 21.6 | 5.85 | 281666.2214
96 | 14600 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 14600 | 5.12 | 4.8 | 1.2 | 0.4 | 14600 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 108480 |  |  |  |  | 14600 | 4600 | 4645.08 | 1059.8893 | 22.08 | 5.98 | 287399.2507
97 | 14700 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 14700 | 5.12 | 4.8 | 1.2 | 0.4 | 14700 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 109610 |  |  |  |  | 14700 | 4700 | 4746.06 | 1082.9304 | 22.56 | 6.11 | 293256.9111
98 | 14800 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 14800 | 5.12 | 4.8 | 1.2 | 0.4 | 14800 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 110740 |  |  |  |  | 14800 | 4800 | 4847.04 | 1105.9714 | 23.04 | 6.24 | 299239.2025
99 | 14900 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 14900 | 5.12 | 4.8 | 1.2 | 0.4 | 14900 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 111870 |  |  |  |  | 14900 | 4900 | 4948.02 | 1129.0125 | 23.52 | 6.37 | 305346.125
100 | 15000 | 567.86 | 34.56 | 876.56 | 0 | 308.7 | 5687.65 | 34.56 | 5653.09 | 0 | 876.54 | 987.65 | 15000 | 5.12 | 4.8 | 1.2 | 0.4 | 15000 | 854 | 126 | 142 | 4 | 4 | 1122 | 8 | 113000 | 56500 |  |  |  | 15000 | 5000 | 5049 | 1152.0536 | 24 | 6.5 | 311577.6786 | 311577.6786
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project
End of project | end of project | end of project | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | #VALUE! | #VALUE! | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of project | end of proejct | end of project | end of project | end of project |  |  |  |  | end of project | end of project | end of project | end of project | end of project | end of project | end of project